## Project Timeline
DCCEEW Investment Pipeline Tool — Project Timeline
DCCEEW NSW ¦ 2026-04-07 to 2026-06-27
|  |  | April 2026 |  |  |  | May 2026 |  |  |  | June 2026
# | Item | Duration | 06 Apr | 13 Apr | 20 Apr | 27 Apr | 04 May | 11 May | 18 May | 25 May | 01 Jun | 08 Jun | 15 Jun | 22 Jun
1 | Discovery & Design | 2 wks | Discovery & Design
2 | Core Build | 5 wks |  |  | Core Build
3 | UAT & Refinement | 3 wks | [7 empty] | UAT & Refinement
4 | Go-Live & Handover | 2 wks | [10 empty] | Go-Live & Handover
Payment Milestones
M1 | Project Kickoff (10%) | 2026-04-07 | *
M2 | Design Sign-Off (20%) | 2026-04-18 |  | *
M3 | Core Build Complete (30%) | 2026-05-23 | [6 empty] | *
M4 | UAT Sign-Off (20%) | 2026-06-13 | [9 empty] | *
M5 | Go-Live (20%) | 2026-06-27 | [11 empty] | *
Legend
| Discovery & Design | 2026-04-07 to 2026-04-18
| Core Build | 2026-04-21 to 2026-05-23
| UAT & Refinement | 2026-05-26 to 2026-06-13
| Go-Live & Handover | 2026-06-16 to 2026-06-27
| * Milestone | Payment milestone due date

## Config
Project Estimation
Project Name | DCCEEW Investment Pipeline Tool
Client | DCCEEW NSW
Version | V2
Date | 2026-04-01
Prepared By | James Diekman
Model | Fixed Price (Days-Per-Phase)
Financial Year | FY26
GST | 10%
Discount | 0
Rate Card
Rate Band | Daily Rate | Hourly Rate
Principal | 2163 | 270.38
Senior | 1963 | 245.38
Associate | 1680 | 210
Junior | 1450 | 181.25
Risk-Weighted Contingency
Solution Area | Contingency %
Project Management | 5%
Setup and Design | 5%
Development | 5%
Integration | 5%
Data Migration | 5%
Testing | 5%
UAT Support | 5%
Go-Live / Cutover | 5%
Handover / Transition | 5%
Training | 5%
Managed Services | 5%
* Flat contingency override: 5%

## Estimate
Phase | Objective | Function | Rate Band | Solution Area | Days | Estimate | Contingency % | Estimate Inc. Contingency
Discovery & Design | Project kickoff, stakeholder alignment, requirements confirmation, UAT plan | Project Manager | Senior | Project Management | 3 | 5889 | 5% | 6183.45
| Solution design, Power Pages architecture, Entra ID spike, wireframes for wizard, approval and dashboard pages | Power Platform Developer (Lead) | Senior | Setup and Design | 3 | 5889 | 5% | 6183.45
| Environment setup, portal provisioning, theme and branding, navigation structure | Power Platform Developer | Associate | Setup and Design | 2 | 3360 | 5% | 3528
Core Build | Sprint management, fortnightly client demos, scope management | Project Manager | Senior | Project Management | 3 | 5889 | 5% | 6183.45
| 5-step initiative submission wizard with validation, Entra ID auto-fill, save-as-draft, security model and web roles | Power Platform Developer (Lead) | Senior | Development | 7 | 13741 | 5% | 14428.05
| Sponsor approval portal page (review, approve/reject with comments), Pipeline Manager and ELT decision dashboard with scoring overview | Power Platform Developer (Lead) | Senior | Development | 3 | 5889 | 5% | 6183.45
| Power Automate: sponsor approval workflow, status change notifications, email alerts on submission/changes | Power Platform Developer (Lead) | Senior | Development | 2 | 3926 | 5% | 4122.3
| Excel upload Power Automate flow with mapping template, data validation and error handling for bulk initiative import | Power Platform Developer (Lead) | Senior | Data Migration | 1 | 1963 | 5% | 2061.15
| Entity lists with Group/Agency filtering, search, initiative views per role (My Initiatives, All Initiatives, Pipeline view) | Power Platform Developer | Associate | Development | 4 | 6720 | 5% | 7056
| Basic visual reporting: pipeline status charts, initiative counts by category/agency, scoring summary views for sector leads and admin | Power Platform Developer | Associate | Development | 3 | 5040 | 5% | 5292
| Prioritisation scoring (7 fields, weighted calculation), audit logging, hyperlinks to supporting documentation | Power Platform Developer | Associate | Development | 3 | 5040 | 5% | 5292
UAT & Refinement | UAT coordination, test script facilitation, defect triage | Project Manager | Senior | UAT Support | 1 | 1963 | 5% | 2061.15
| Bug fixes from UAT (2 rounds), performance hardening, security testing across all portal pages | Power Platform Developer (Lead) | Senior | Testing | 4 | 7852 | 5% | 8244.6
| UAT support, bug fixes, data validation, regression testing on reporting and approval flows | Power Platform Developer | Associate | Testing | 3 | 5040 | 5% | 5292
Go-Live & Handover | Go-live management, project closure, lessons learned | Project Manager | Senior | Go-Live / Cutover | 1 | 1963 | 5% | 2061.15
| Production deployment, initial Excel data load (~140 initiatives), smoke testing, hypercare | Power Platform Developer (Lead) | Senior | Go-Live / Cutover | 2 | 3926 | 5% | 4122.3
| Admin guide, Excel upload template documentation, knowledge transfer session | Power Platform Developer | Associate | Handover / Transition | 1 | 1680 | 5% | 1764
TOTAL |  |  |  |  | 46 | 85770 |  | 90058.5
[5 empty] | GST | 8577 |  | 9005.85
[5 empty] | Total Inc. GST | 94347 |  | 99064.35

## Resource Summary
Summary by Function
Function | Rate Band | Daily Rate | Total Days | Estimate | Estimate Inc. Contingency | % of Total
Power Platform Developer (Lead) | Senior | 1963 | 22 | 43186 | 45345.3 | 50.35%
Power Platform Developer | Associate | 1680 | 16 | 26880 | 28224 | 31.34%
Project Manager | Senior | 1963 | 8 | 15704 | 16489.2 | 18.31%
TOTAL |  |  | 46 | 85770 | 90058.5 | 100%
Summary by Solution Area
Solution Area | Contingency % | Total Days | Estimate | Estimate Inc. Contingency | % of Total
Development | 5% | 22 | 40356 | 42373.8 | 47.05%
Testing | 5% | 7 | 12892 | 13536.6 | 15.03%
Project Management | 5% | 6 | 11778 | 12366.9 | 13.73%
Setup and Design | 5% | 5 | 9249 | 9711.45 | 10.78%
Go-Live / Cutover | 5% | 3 | 5889 | 6183.45 | 6.866%
Data Migration | 5% | 1 | 1963 | 2061.15 | 2.289%
UAT Support | 5% | 1 | 1963 | 2061.15 | 2.289%
Handover / Transition | 5% | 1 | 1680 | 1764 | 1.959%
TOTAL |  | 46 | 85770 | 90058.5 | 100%

## Weekly View
Weekly Resource View — Fixed Price (Days-Per-Phase)
Values = days per week per function. Colour: Green < 2.5d, Amber 2.5–4d, Red > 4d
Week Commencing | Phase | Power Platform Developer | Power Platform Developer (Lead) | Project Manager | Total Days | Total Cost
06 Apr 2026 | Discovery & Design | 0.9 | 1.3 | 1.3 | 3.5 | 6728
13 Apr 2026 | Discovery & Design | 1.1 | 1.7 | 1.7 | 4.5 | 8410
20 Apr 2026 | Core Build | 1.7 | 2.2 | 0.5 | 4.4 | 8035
27 Apr 2026 | Core Build | 2.1 | 2.7 | 0.6 | 5.4 | 10043
04 May 2026 | Core Build | 2.1 | 2.7 | 0.6 | 5.4 | 10043
11 May 2026 | Core Build | 2.1 | 2.7 | 0.6 | 5.4 | 10043
18 May 2026 | Core Build | 2.1 | 2.7 | 0.6 | 5.4 | 10043
25 May 2026 | UAT & Refinement | 0.9 | 1.1 | 0.3 | 2.3 | 4244
01 Jun 2026 | UAT & Refinement | 1.1 | 1.4 | 0.4 | 2.9 | 5305
08 Jun 2026 | UAT & Refinement | 1.1 | 1.4 | 0.4 | 2.9 | 5305
15 Jun 2026 | Go-Live & Handover | 0.4 | 0.9 | 0.4 | 1.7 | 3364
22 Jun 2026 | Go-Live & Handover | 0.6 | 1.1 | 0.6 | 2.3 | 4205
TOTAL |  | 16 | 22 | 8 | 46 | 85770

## Forecast Export
Project | Client | Version | Model | Function | Rate Band | Week Commencing | Estimated Days | Daily Rate | Estimated Cost
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer | Associate | 2026-04-06 | 0.9 | 1680 | 1495
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer (Lead) | Senior | 2026-04-06 | 1.3 | 1963 | 2611
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Project Manager | Senior | 2026-04-06 | 1.3 | 1963 | 2611
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer | Associate | 2026-04-13 | 1.1 | 1680 | 1865
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer (Lead) | Senior | 2026-04-13 | 1.7 | 1963 | 3278
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Project Manager | Senior | 2026-04-13 | 1.7 | 1963 | 3278
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer | Associate | 2026-04-20 | 1.7 | 1680 | 2806
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer (Lead) | Senior | 2026-04-20 | 2.2 | 1963 | 4260
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Project Manager | Senior | 2026-04-20 | 0.5 | 1963 | 982
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer | Associate | 2026-04-27 | 2.1 | 1680 | 3494
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer (Lead) | Senior | 2026-04-27 | 2.7 | 1963 | 5320
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Project Manager | Senior | 2026-04-27 | 0.6 | 1963 | 1217
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer | Associate | 2026-05-04 | 2.1 | 1680 | 3494
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer (Lead) | Senior | 2026-05-04 | 2.7 | 1963 | 5320
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Project Manager | Senior | 2026-05-04 | 0.6 | 1963 | 1217
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer | Associate | 2026-05-11 | 2.1 | 1680 | 3494
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer (Lead) | Senior | 2026-05-11 | 2.7 | 1963 | 5320
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Project Manager | Senior | 2026-05-11 | 0.6 | 1963 | 1217
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer | Associate | 2026-05-18 | 2.1 | 1680 | 3494
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer (Lead) | Senior | 2026-05-18 | 2.7 | 1963 | 5320
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Project Manager | Senior | 2026-05-18 | 0.6 | 1963 | 1217
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer | Associate | 2026-05-25 | 0.9 | 1680 | 1445
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer (Lead) | Senior | 2026-05-25 | 1.1 | 1963 | 2238
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Project Manager | Senior | 2026-05-25 | 0.3 | 1963 | 569
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer | Associate | 2026-06-01 | 1.1 | 1680 | 1798
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer (Lead) | Senior | 2026-06-01 | 1.4 | 1963 | 2807
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Project Manager | Senior | 2026-06-01 | 0.4 | 1963 | 707
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer | Associate | 2026-06-08 | 1.1 | 1680 | 1798
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer (Lead) | Senior | 2026-06-08 | 1.4 | 1963 | 2807
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Project Manager | Senior | 2026-06-08 | 0.4 | 1963 | 707
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer | Associate | 2026-06-15 | 0.4 | 1680 | 739
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer (Lead) | Senior | 2026-06-15 | 0.9 | 1963 | 1747
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Project Manager | Senior | 2026-06-15 | 0.4 | 1963 | 864
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer | Associate | 2026-06-22 | 0.6 | 1680 | 941
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Power Platform Developer (Lead) | Senior | 2026-06-22 | 1.1 | 1963 | 2179
DCCEEW Investment Pipeline Tool | DCCEEW NSW | V2 | Fixed Price (Days-Per-Phase) | Project Manager | Senior | 2026-06-22 | 0.6 | 1963 | 1099

## Payment Milestones
# | Milestone | % of Total | Amount Ex GST | Amount Inc GST | Due Date | Acceptance Criteria
1 | M1 - Project Kickoff | 10% | 9006 | 9906 | 2026-04-07 | Contract signed, environments confirmed, kickoff completed
2 | M2 - Design Sign-Off | 20% | 18012 | 19813 | 2026-04-18 | Signed requirements register, wireframes approved for wizard, approval pages and dashboards
3 | M3 - Core Build Complete | 30% | 27018 | 29719 | 2026-05-23 | Portal, wizard, approval pages, reporting views, Excel upload flow deployed to UAT
4 | M4 - UAT Sign-Off | 20% | 18012 | 19813 | 2026-06-13 | Client UAT completion form signed, all P1/P2 defects resolved
5 | M5 - Go-Live | 20% | 18012 | 19813 | 2026-06-27 | Production deployed, initial data loaded via Excel upload, handover complete
| TOTAL | 100% | 90058 | 99064